## Notes
A strategy for improving waste data in Scotland
The waste data strategy aims to deliver Scotland’s current and future waste data needs as we move towards a more resource-focused future. It outlines what we will achieve and how we are going to co-ordinate and deliver a plan that will support Scotland’s transition to a more circular economy. You can find out more here: https://www.environment.gov.scot/data/waste-data-strategy/#strategy The strategy is underpinned by an action plan. This sets out five stategic aims, the detailed actions needed to deliver these aims and identifies the lead organisation and broad timescales for each action. The waste data strategy delivery board and the waste data practitioners group have contributed to the development of the action plan and are responsible for monitoring its progress.
Published November 2018
Version 1.0

## Action plan
Waste Data Strategy Action Plan
Strategic aim | Detailed actions | Lead organisation | Start date | End date
Track waste from the point of production to its final destination | Deliver an electronic system to track waste across the UK
| Provide technical, financial and administrative support to the UK waste tracking project | UK agencies/governments | 2017 | 2021
Preparation for a waste tracking system in Scotland
| Review and if necessary amend Duty of Care legislation to align with the needs of a waste tracking system | SG | 2017 | 2019
| Review and if necessary amend hazardous waste legislation (including charging) to align with the needs of a waste tracking system | SG | 2017 | 2019
| Review impact of waste tracking on SEPA systems and processes (including licence/permit conditions, data returns etc) and ensure future developments align with waste tracking requirements | SEPA | 2018 | 2019
| Ensure stakeholders in Scotland are consulted and informed about the UK waste tracking project | SEPA | 2017 | 2021
| Review LIFE SMART Waste crime detection toolkit for potential to be used with waste tracking data | LIFE SMART Waste project | 2019 | 2020
Other tracking waste actions
| Investigate the option for WasteDataFlow to record/report the complete path of waste movements | SEPA | 2018 | 2018
| Investigate mandatory reporting of next destination in SEPA site returns | SEPA | 2019 | 2020
Provide data to support the circular economy | Waste composition
| Complete options appraisal on future waste composition study approach for Scotland covering both household and C&I wastes | ZWS | 2018 | 2018
| Develop methodology for testing composition of residual/mixed waste at the final disposal point (landfill, incineration etc) | ZWS | 2018 | 2019
| Understand the composition of non-target materials in MRF inputs and communicate findings to local authorities, householders and businesses | SEPA | 2018 | 2018
| Review density conversion factors for priority waste streams to ensure factors are still appropriate | SEPA | 2019 | 2021
New metrics/measurement
| Investigate a range of metrics to measure progress towards a circular economy in Scotland and develop a suitable national measure | ZWS | 2018 | 2019
| Develop ‘materials flow’ approach to track materials moving through the economy and into the waste stream | ZWS | 2018 | 2020
| Identify and prioritise materials for trialling the 'materials flow' approach | ZWS | 2020 | 2021
| Investigate how the UK waste tracking service can be expanded to incorporate non-waste materials | SEPA | 2022 | 2025
| Develop a business level indicator tool for businesses to benchmark their circular economy performance against a sector/industry/national standard | ZWS | 2019 | 2020
Monitor progress against Scottish Government and EU waste targets | Scottish targets
| Continue to monitor and publish progress towards waste targets | SEPA | 2018 | 2025
| Develop a methodology for the baseline and on-going monitoring of the 33% food waste target | ZWS | 2017 | 2018
| Establish carbon intensity of EfW in Scotland to inform progress towards climate change targets | SEPA | 2018 | 2019
| Improve information on flaring and gas capture at landfill sites to monitor climate change targets | SEPA | 2018 | 2019
| Investigate how to improve data on 'preparing for reuse' | SEPA | 2019 | 2020
EU targets
| Review reporting requirements of the EU 2018 Circular Economy package and assess our ability to meet them | SG | 2018 | 2019
Improve the quality of data reported by businesses and local authorities | Training and guidance
| Carry out user research to understand issues faced by data providers and provide guidance in a format that meets their needs eg workshops, webinars | SEPA | 2018 | 2019
| Align data reporting guidance with SEPA's sector approach to regulation where appropriate | SEPA | 2019 | 2020
| Develop and publish standard data management principles | SEPA | 2018 | 2019
| Develop a standard protocol for local authority use when collecting data from their waste collection contractors | SEPA | 2018 | 2018
| Improve EWC code guidance and be more proactive in providing advice on use of the EWC | SEPA | 2018 | 2020
Enforcement
| Introduce stronger enforcement measures to encourage more accurate and timely reporting of data | SEPA | 2018 | 2020
Improve the way we interact with data customers | Working with others
| Invite a wider range of businesses, agencies and potential partners to join the Waste Data Practitioners Group and hold regular events | WDSD Board | 2018 | 2025
| Work with local authorities to enhance the relevance and benefits of the annual WDF user group | SEPA | 2018 | 2018
| Establish clear roles and responsibilities for everyone involved in the data chain | SEPA | 2018 | 2019
Enhanced data
| Improve metadata associated with waste data | SEPA | 2018 | 2020
| Develop plans to publish as much of the raw waste data that SEPA collects as possible, e.g. Annex VII, SWCN, site returns and exemptions data | SEPA | 2018 | 2020
| Investigate how waste data could be linked to economic, financial or geographical data to provide more meaningful information | ZWS | 2020 | 2021
| Carry out user research to understand the needs of data users and review current data reporting in light of the findings | WDSD Board | 2018 | 2019
| Produce Spotfire tool for visualising WDF data for use by local authorities and public users | SEPA | 2018 | 2019
| Publish NHS waste data by individual health board | NHS | 2018 | 2020
Publications
| Develop publication calendar for waste data, identify opportunities to align timescales, and agree main messages to communicate | SEPA | 2018 | 2018
| Identify ways to better communicate waste data to the public, eg tell stories, appropriate use of infographics | WDSD Board | 2018 | 2019
| Set up a process to notify data providers and data users when data is published | SEPA | 2018 | 2018
| Review options for presenting data on incineration capacity | SEPA | 2019 | 2019
| Produce list of EWC codes associated with SEPA waste type reporting categories (from Waste Statistics Regulation) and provide a link in all future publications | SEPA | 2018 | 2018
| Review, identify and develop new case studies on SEWeb, e.g. to show examples of systems development and explain why organisations like SEPA collect data | SEPA | 2018 | 2020
| Identify opportunities to publish more waste data as Official Statistics and National Statistics | SEPA | 2018 | 2020